## Year 1
Bridging IDD/Aging Grant Workplan Template 2022
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #3: May-June | Step 1: FRIDGE MAGNETS: free community resource for anyone who wants it. To be distributed across the state | Amelia to have the lists ready by the end of June, July magnet approval, August magnet purchased and October 2022 magnets start to be sent out | magnet to be approved at next SAT meeting July 29 | Amelia | Magnet design has been created, to be reviewed at next SAT meeting. Vistaprint cost for 5000 magnets is 600 dollars includes shipping size 3x2
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | to have updates completed on the ADRC website by September 2022 | SAT group met and looked at the ADRC website. Suggestions included adding a section for individauls with disabilities and then listing out resources. Philip also wanted to include a section on health specific to women's health and reproduction. Email was sent to Caroline about the website changes we are waiting for approval | Philip | Mary Brogan from DD Division has added resources to her website on aging and dementia care, linking it to Catholic Charities Hawaii
| Step 3: DEMENTIA CARE AND EDUCATION: Amelia to attend Health Matters information meeting | completed by July 2022 | Amelia attended the Health Matters training and will provide information on the training at July's meeting to the SAT. Amelia sent the Health Matters training to Easterseals and Daintry sent it to the DOE to see if anyone was interested in applying for it. It was determined that the training must be applied for by each agency, that supports individuals with DD/ID | Amelia | completed
| Step 4: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | Up and running statewide by June 2024 | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Looking for 5 students on Kauai for 2023 | Amelia | get approval from SAT to create internship program. SAT approved internship program. Mary Brogan suggested students who are interested in the internship program to then roll into her new training program.
| Step 5: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Training | training to be held end of 2023/ or early 2024 | That agencies, medical professionals, and families will attend the conference. Hoping to get at least 5 people to become traininers in Hawaii on third day of conference | Amelia / Jody / Melissa
Potential Obstacles and Notes: waiting for ADRC to complete their website upgrades could take longer than original timeline. Cost of the NTG conference will exceed grant budget.
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #4: July, August, September | Step 1: FRIDGE MAGNETS: Amelia to create a list of resources with input from SAT memebers and lists specific to each island. SAT meets monthly | 2022-07-01 | SAT to approve revised fridge magnet, fridge magents to then be purchased by September 2022 | Amelia | Fridge magnets were approved and 5000 will be purchased. Amelia got 3 quotes for the magnets all of the prices were similar approximately $1000 with shipping. Suggestions for two Hawaiian locations were provided at the last SAT meeting. However, both locations do not provide printing of fridge magnets. Kauai SAAC to pay for fridge magnets.
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | to have updates completed on the ADRC website by September 2022 | Philip and Daintry emailed Caroline about changes to website. Waiting to hear from Caroline about changes | Philip/ Daintry | Caroline was able to attend our last meeting. She said that the contract for the website developer is in the process of being renewed but that she would follow up with the website developer to see if he could make the changes we are requesting. She will get back to us on a timeline for the changes to be made to the ADRC website. We are waiting to hear back from Caroline before we purchase the fridge magnets so that we do not send them out before the information is up on the webpage. S
| Step 3: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | Up and running statewide by June 2024 | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Looking for 5 students on Kauai for 2023 | Amelia | Amelia has emailed 3 high schools on Kauai. Kauai High and Waimea High are both intersted. I talked to a teacher from Waimea High school on 7/18. Who definitely wants to offer the internship program, she will send me and email with counselor and teacher contact information so I can keep them updated on the implementation timeline. Kauai High principal asked for a meeting, dates were sent but no response as of 7/19 on a meeting date and time. Amelia met with Gina Berlesky, she suggested Open Future Learning as training/background information program for interns. She also suggested mentor for the interns so they had someone to talk to and follow up with on how internship went. Gina is willing to be this perosn. Amelia to start free Open Future Learning trial August 1, 2022. Amelia to look into AER funds for program. Amelia also emailed all of the high schools on Mauai. And has a meeting setup with St. Anthony's Prepatory School for August. Amelia is also meeting with Island School to discuss the internship program. Amelia reached out to Easterseals on Kauai about the internship program to find out what the process would be for them to take on interns. Amelia is currently going through the open future learning modules to determine which ones would be best for the interns to complete as part of their training. Amelia is working on roles and responsibilites, for intern and DSP. Diantry to determine how to provide the funding stipend of paid internship based on liability. Currently have two Maui schools and two Kauai high Schools. Liability issues have been resolved and Maui ARC can start taking students in October 2022. Amelia met with Easterseals Waimea and they are able to take 2 students on Kauai from Island school in February 2023. We met with the Principal from Island School and we are set to start receving applications in October. Met with St. Anthony's high school, and Arc of Maui. They are all sent to move forward. St. Anthony's will talk to their seniors and see if anyone is interested in partcipating. Hopefully we will be able to get two students in Maui started by the end of October. Ka Lima O Maui (ADH) has agreed to move forward with the internship program and Kiehi Charter school also wants to participate. I will follow up with Maui High and Kiehi Charter to see when students can start.
| Step 4: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Conference | August 8, meeting with NTG | Amelia, Philip and Jody to meet with NTG and plan conference | Amelia/Jody | meeting has been scheduled with NTG for August 8, 2022 current cost of conference is $15k, next meeting and first payment to be made August 30. Daintry and Amelia attended meeting on August 29, to create MOA and get other information on the training. They will be sending Amelia their requirements and will draft up the MOA and send it to us. Daintry and Amelia met with the NTG people. We discussed eqipmenet requirements and other technology they will need for the event. We are waiting for the MOA from them. Veterans center in honolulu has been booked for the event November 1-3. LexiconUSA quote has been received for the hybrid eqipment needed. Hybrid technology eqipement has been invoiced and sent for payment from SAAC.
Potential Obstacles and Notes: liability issues with the ADH programs has slowed progress with the internship program. Along with getting the ADRC website updated. Fridge magnets are delayed until ADRC website is updated.

## Year 2
Bridging IDD/Aging Grant Workplan Template 2023
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #1: October, November, December 2022 | Step 1: FRIDGE MAGNETS: free community resource for anyone who wants it. To be distributed across the state | October-December 2022 | Distribution of 5000 fridge magnets by agencies and community events | Amelia | cost $1200 to by paid for by DD Council/ SAAC. On hold until the ADRC Website is updated
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | December 2022 | ADRC website should be updated with basic links to other information on DD/ID and Aging (DD Council, CDS, Catholic Charities, DD Divison) | Philip/Daintry | We created a list of resources for the website. Should be updated by December 2022. Sent in a list of items and name of what to class the page for the ADRC. Waiting for it all to be uploaded. List of categories for the website: Services and Agency Providers Agency providers, Care Services, Advocacy, Technology, Health Finance, Community Resources:
| Step 3: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | December 2022 | Amelia to have a list of schools who will participate in the grant program from Kauai and Maui. SAT to determine how many students to have participate. SAT to create outline of the program and cost / person based on minimum wage (new minmum wage) approx $800/student for 40 hours of internwork over 2 weeks and 4.5 hours of online modules | Amelia | We have 3 spots available on Maui. We are waiting for 2 students from St. Anthony's to apply they will either start Dec, or January 2023. Meeting with Kihei Charter School Nov. 1, to see if they want their students to participate. Kihei had 1 student who wanted applied but did not follow through with completing the interview process. We are waiting for Island School on Kauai applications. School is behind but hopes to have applications by middle December. New flyer has been created and content about the internship program has been put on the DD Council website. https://hiddcouncil.org/internship-opportunities/ and we created a flyer for schools. It is also on the website available to download. | Website Link: Internship Program
| Step 4: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Conference | November 2022 | Amelia, Philip and Jody to work with NTG to find date for Dementia training program. Funding to be secured by grant, downpayment to be made. | Amelia, Daintry | We met with the NTG and we got the invoice for the next $5,000.00 we sent it to NACDD. We received the flyer and are editing it, and working on getting continuing education credits approved for social workers, and nurses.
| Step 5: Adult Protective Services Training on DD/ID | Spring 2023 | To coordinate training with Adult protective services and DD Divison or other knoweldgable entity to educate social workers on developmental disabilities | Jody | Jody is working with Adult Protective Services to provide training on dementia care. We discussed seeing if we can add in education to the social workers about developmental disabilities. Meeting to be held November 14. Not something we are adding to the grant any longer. Will be something that the council supports independently.
Potential Obstacles and Notes: waiting for ADRC to complete their website upgrades could take longer than original timeline. Fridge magnets on hold until ADRC website is updated. Getting students to sign up for the internship program. Has been more difficult than anticipated. Even with a stipened students are not as intersted as we thought. Possible thought to open it up to college/university students in a relevent field.
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #2: January, February, March 2023 | Step 1: FRIDGE MAGNETS: free community resource for anyone who wants it. To be distributed across the state | March 2023 | next round of magnets to be purchased and then distributed across the state | Amelia | 200 magnets were purchase for Day at the Capitol event and distributed to legislators and given out at community events on Kauai.
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | March 2023 | More changes made to the ADRC website to include a large box that says Disability Resources and have a comprehensive list of at leat 15 resources | Amelia | still waiting for ADRC to get website updated
| Step 3: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | February-March 2023 | Amelia to meet with all high schools wanting to participate in the internship program. Provide the schools with the application form/link for students to complete. Looking for a minimum of 10 students across Kauai and Maui. Application Deadline March 31, 2023. | Amelia | We have one intern on Kauai. She is currently working on the modules and will attend Waimea Easterseals AHD in February 21-24. We have an applicant for Maui Rachel to do 60 hours during the summer. And received second application for Spring Break 20 hours for Margie Sana on Maui.
| Step 4: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Conference | March 2023 | Location of event to be confirmed and deposit paid if required. Determine how people will register for conference, and create flyers for event | Amelia, Philip, Jody | Location Cost and food $1000-$5000. We are working on obtaining CEU's for social workers and nurses. We met with the NTG in January, and they are working on getting us the updated MOA. Amelia has met with Lori Henning for Hawaii Health Association. They are willing to do the CEU's and will send updated cost.
Potential Obstacles and Notes: ADRC website may take longer to be updated. Cost of NTG conference location, technology and translation services needed for conference
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #3: April, May, June 2023 | Step 1: FRIDGE MAGNETS: free community resource for anyone who wants it. To be distributed across the state | completed for the year | To have at least 50 braille magnets distributed by the end of 2023. | Amelia | We continue to distribute the magnets that we have previously made and are looking at how to have braille put on some of the magnets.
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | June 2023 | ADRC website updated with the new county booklets with disability resource list and free printable information form | Amelia and Philip | still waiting for it to be updated
| Step 3: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | June 2023 | completed our first cohort of interns on Kauai and Maui. Feedback collected from students and schools for next years planning | Amelia | Currently we have one intern scheduled for the summer on Kauai to complete up to 100 hourrs. She is a returning intern from her February internship through Island School. We have two interns for Maui during the summer. One is from Keihi Charter school she will complete 60 hours for school (unpaid). We have a returning intern Margie to complete 75 hours during the summer. Both returning interns are now interested in carreers that can support individauls with IDD.
| Step 4: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Conference | June 2023 | To obtain the materials needed for CEU's. The save the date flyer is created and ready for distribution. Sign up fo the conference will open in August 2023. | All agencies to send out flyers and promote the conference | Had a meeting with NTG on April 24. We are working with the Hawaii Health Assicaiotn for CEUs and are currently waiting for Kathryn and Kathie to send the information needed.
| Step 5: Pamphlets: ADRC County booklets to be updated with DD/ID information for each county and distributed | June 2023 | Booklets have been updated and are in production to be distributed by each county | Amelia and Philip | Philip has reached out to Caroline to see if we can use ADRC County booklets. Caroline said we could update the booklets. We have met and discussed them. Amelia is putting together the updated lists based on categories created by the group. Amelia has emailed out the updated list and it will be discussed at our next meeting. List have been finalized and Philip was able to send out the request for the booklets to be updated. Both Kauai and Hawaii island of Agency on Elderly Affairs said they would work on updating their books with the new information.
| Step 6: Individual Information Sheet: information sheet for the fridge that has medical info, medications, communication needs etc…. | May 2023 | Information sheet to be created and SAT approved for the booklets | Amelia and Melissa | Amelia has found some templates that can be modified for our needs
| Step 7: Partnering with Alzheimer's Association for June. June is Alzheimer's Awarness month | June 2023 | Attend the proclamation ceremony across two islands and support the Maui Rally. | Amelia and Daintry | Amelia and Daintry have been meeting with the Alzheiemer's association to build our relationship with that organization. June is Alzheimer's awarness month. And they will becoming to Kauai to meet with the Mayor and have a proclamation signed. Amelia will support this effort and if it works out have a self-advocate attend the signing. Also support their Maui rally about Alzheimer's medication avaialbility. We will encourage ADAH programs to attend and support the rally.
Potential Obstacles and Notes: we continue to wait for the ADRC website to be updated. No date set yet for the updated Kauai and Hawaii island booklets to be rolled out. We have not yet started the individual information sheet. Due to other projects taking up more time.
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #4: July, August, September 2023 | Step 1: FRIDGE MAGNETS: free community resource for anyone who wants it. To be distributed across the state | Completed for this year | We have purchased 1400 fridge magents. To be distributed state wide during SAT community events | Amelia/Daintry
| Step 2: UPDATE ADRC WEBSITE: to add to ADRC website information about disabilities and to link them to CDS, DD Council and other services | August 2023 | All revisions/updates of current SAT information is on the ADRC website | Amelia | Waiting for the website to be updated. They have all of the information. First part has been updated. Tile has been put onto the website. Feedback has been given to Chris with the list to update the information.
| Step 3: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT PROFESSIONALS: Amelia will reach out to Kauai Department of Ed, to see if they are interested in assisting with this internship program | August 2023 | Amelia to reach out to new schools on Big Island and Oahu to impelment internship program statewide. | Amelia | We have had 4 internships over the summer. Three in Maui and one on Kauai. Amelia will reach out to high schools on Oahu and Hawaii Island towards the end of August along with the adult day health centers.
| Step 4: Plan a National Task Group on Intellectual Disabilities and Dementia Care Practices Conference | September 2023 | Amelia, Philip, Jody to finalize any conference details. Create swag bags, and conference agendas. | Amelia, Philip, Jody | CEU requirments have been submitted to Hawaii Health Association. We are waiting for their reply on if they will allow nursing and social work CEU. Food has been quoted and we have discussed swag bag items. Each agency is to provide swag items to DD Council by September. Registration to open August 1, 2023.
| Step 5: Pamphlets: ADRC County booklets to be updated with DD/ID information for each county and distributed | August 2023 | Booklets to be available across each island and distrubuted to agencies and at community events/ places (resource kiosks) | Amelia | The Hawaii Island booklet has been updated and uploaded to their website. We are following up with the Kauai County to see if they have implemented the changes yet.
| Step 6: Individual Information Sheet: information sheet for the fridge that has medical info, medications, communication needs etc…. | 2023-09-01 | Not yet started | Amelia | We have not yet started this project
Potential Obstacles and Notes: issues with conference location, making sure enough people sign up. Getting people who want to become EDSD trainers
Accomplishments
Completed the booklet lists both Kauai and Hawaii Island have implemented our reccomendations
handed out 400 magnets
Created a new relationship with Alzheimer's association
Website has been updated- More changes to come
The SAT has been a crucial support for providing information to Maui during the fires. SAT has come together to support families and provide resources where needed

## Year 3
Bridging IDD/Aging Grant Workplan Template
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Marketing/Educational Item
Quarter #1: October, November, December 2023 | FRIDGE MAGNETS: By December 2023, the SAT will have distributed 1400 fridge magnets statewide. | more magnets to be purchased and give out during the NTG training | to continue to distribute magnets each year of the grant. To ensure people know to go to the ADRC for information. Increase community knoweldge of resources | Amelia | Magnet design has been created, and approved. Braille magnets to be created and next batch of magnets to be distributed.
Goal Two: Website Development
| UPDATE ADRC WEBSITE: By December 2023, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2023. | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Debbie | Website has the tile and some resources available. We are waiting for additional changes to be made.
Goal Three: Training and Education
| DEMENTIA CARE AND EDUCATION: NTG Training. By November 2023, the SAT will have held the 3 day NTG training on Oahu, providing training to at least one person on each island and a total of 75 individuals statewide. | completed November 2023 | NTG traininers will provide 2 day training and 3rd day option train the trainer. To increase community knoweldge and hopefuly systems change on screeings for individuals with IDD and Dementia | Amelia | getting together the registration lists, following up with the caterers and making sure we have all of the technology needed. Additonal swag bag items to be compiled and anything that needs to be mailed to registrants is to be done. The training was held, and post surveys were positive. Everyone learned alot and really liked the training. We are now going to add two items to our work plan to continue this education including additional condensed trainings and a resource booklet on brain health, signs and symptoms and hawaii resources.
Goal Four: Workforce Development
| HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By December 2023, Amelia will identify at least 3 new adult day health programs that want to participate in the internship program across Oahu and Hawaii Island. | Up and running statewide by June 2024. We will have 10 students statewide participating in the internship program for summer of 2024. | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Up and running on Maui and Kauai. Will hopefully have additional schools on Oahu and Hawaii island by December 2023 and placements available. | Amelia | revisions to the requirements need to be made to add in 2 step TB test. This will be targeted in the new year. We are looking at having the internship during the summer only.
Goal Five: Printable Form
| One page all about me for fridge. By December 2023, the SAT will have identified the information that they want to include on the form and the form will be ready for distirbutation. | to be completed by December 2023 | Aging individuals with IDD will have a one page document on their fridge that outlines medical information to aid in their care for emergency response. | Amelia | We have decided to add onto this project. Exanding it to include emegerncy prepardness information. We will look at creating two pages instead of one, and look at offering Feeling Safe beinng Safe trainings.
Goal Six: Collaboration/ Networking/Strategic Planning
| The SAT will continue to meet and assist with the Maui Wild Fire emergency | The SAT will continue to meet as needed to address any issues that arise for individuals with IDD due to the Maui Wild Fires | To insure that people with IDD and Kupuna have resources and supports needed. | Daintry | Currently, we have been hosting weekly meetings. In November they were moved to be part of other Maui Wildfire meetings that were also occuring. They have worked on obtaining equipment for those who needed it, and communication devices. We aslo insured supports were provided to those needing ASL interpreters.
Potential Obstacles and Notes: waiting for ADRC to complete their website upgrades could take longer than original timeline. We have not yet started thee All About me page, it has been postponed and we are looking at expanding it to add in emergency prepardness due to the Maui wild fires. 7
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Marketing/Educational Item
Quarter #2: January, February, March 2024 | Step 1: FRIDGE MAGNETS: By December 2024, the SAT will have distributed 1400 fridge magnets statewide. | all current magnets to be distrbuted by the end of December 2024. | To increase the awarness of the ADRC website and agency as a place for information for families across Hawaii. | Amelia | 1400 magnets have been purchased and continue to be distributed statewide during events and to agencies as requested. Once we are out of magnets additional ones will be purchased.
Goal Two: Workforce Development
| Step 2: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By December 2023, Amelia will identify at least 3 new adult day health programs that want to participate in the internship program across Oahu and Hawaii Island. | Up and running statewide by June 2024 We will have 10 students statewide participating in the internship program for summer of 2024. | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Up and running on Maui, Kauai and Oahu. | Amelia | High School Internship program is available on Oahu, Maui and Kauai. Currently we have two students confirmed to start on Oahu in June. We have one student currently going through the interview process on Maui. We had one application for Kauai but were not able to complete the interview process with that applicant. We continue to advertise the program through local high schools. We have three new schools that are providing information to students on the internship program.
Goal Three: Printable Form
| Step 3: One page all about me for fridge. By December 2024, the SAT will have identified the information that they want to include on the form and the form will be ready for distirbutation. | By March 2024, we will have a 1 page emergency information sheet for a person's fridge and will have determiend | Aging individuals with IDD will have a one page document on their fridge that outlines medical information to aid in their care for emergency response. | Amelia | We have created the emergency form. It is one page front and back and includes a functional needs list. We are working on creating an instruction form to go with the worksheet so individuals know how to complete it.
Goal Four: Resource Booklet
| Step 4: Create a resource booklet with brain health information to be distributed statewide. It will include people who are willing to do EDSD screeings, brain health and signs/symptoms to look for and questions to ask your doctor. | By March 2024, we will have a layout and all of the topics chosen for the resource booklet. | Families, caregives and support staff are requesting addiontal information and resources for individuals with IDD and Dementia as an outcome from the NTG training. This booklet will provide them with statewide resources and information. | Amelia | We have started working on this. We are looking at the Rhode Island Resource guides. And have created a list of topics to include in our books. Also based off of feedback from the NTG training. We want to make sure the booklets are in plain language. We have requested that SAAC members submit artwork for the front cover. We will choose the art at our May meeting. We have the booklet content completed and are working on formatting.
Goal Five: Continuing Education
| Step 5: Based off of the NTG training, we will work with agencies who have agreed to provide ongoing trainings on dementia, and create a condensed training that can be completed within 90 minutes or less. We will offer the training. | This has been removed and we will no longet be targeting this goal. |  |  | Catholic Charities of Hawaii a SAT partner received their own Community Care grant and will be the ones in charge of the trainings moving forward.
Goal Six: Website Development
| UPDATE ADRC WEBSITE: By December 2023, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2023. | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Caroline | Website has the tile and some resources available. We are waiting for additional changes to be made. In November the updated resource list was re-sent to the ADRC. We are working on getting the County Agency on Elderly Affairs webpages updated too.
Quarter | Potential Obstacles and Notes: The ADRC only has one person who assists them with their website development. It has taken longer than expected to get the changes made to it. We did not receive as many applications for the internship program as we had hoped. Although some people apply, they do not respond to setup the interivew and move forward with the process. The cost of maintining some of the activities including the fridge magnets and the internship program will be difficult moving forward. We are looking at additional resources (funds) that might be able to assist with the continued cost.
| Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #3: April, May, June 2024 | Goal One: Marketing/Educational Item
| Step 1: FRIDGE MAGNETS: June 2024, the SAT will have given out at least 700 fridge magnets statewide | more magnets to be purchased and give out during community outreach activities by SAT members | to continue to distribute magnets each year of the grant. To ensure people know to go to the ADRC for information | Amelia | We are continuing to distribute the magnets we have. We have putchased a total of 1500 so far. We will continue to distribute them. Once all are distributed we will purchase more.
Goal Two: Workforce Development
| HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By June 2024, we will have at least 5 students signed up for the internship program across the state. | Up and running statewide by June 2024 | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Up and running on Maui and Kauai. Will hopefully have additional schools on Oahu and Hawaii island by December 2023 and placements available. | Amelia | Currently, we have reached out to three of the four major islands. We have interns set to start their internship on Oahu in June. We are in the process of interviewing and setting up another person on Maui. Two other interns applied but did not move forward with the interview process. We have 5 interns this year. Three on Oahu, one on Maui and one on Kauai. We have started looking at how to make the internship program more sustainable moving forward. We are also looking at how to increase the use of college students and practicums at ADH centers.
Goal Three: Printable Form
| One page all about me for fridge. By June 2024, the information page will be available on the ADRC and DD Council websites. | to be completed by December 2024 | Aging individuals with IDD will have a one page document on their fridge that outlines medical information to aid in their care for emergency response. | Amelia | Is currently being finalized. We will hopefully have it approved by the SAT members at the May meeting.
Goal Four: Resource Booklet
| Create a resource booklet with brain health information to be distributed statewide. It will include people who are willing to do EDSD screeings, brain health and signs/symptoms to look for and questions to ask your doctor. | By June 2024, we will have all of the information we want into the booklet and we will work on layout and distritbution | Families, caregives and support staff are requesting addiontal information and resources for individuals with IDD and Dementia as an outcome from the NTG training. This booklet will provide them with statewide resources and information. | Amelia | Is currently being formatted and finalized. Waiting for SAAC members to submit artwork for the front cover, we will make the decision on the artwork at our May meeting.
Goal Five: Website Development
| UPDATE ADRC WEBSITE: By December 2023, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2023. | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Caroline | Website has the tile and some resources available. We are waiting for additional changes to be made. In November the updated resource list was re-sent to the ADRC. We are working on getting the County Agency on Elderly Affairs webpages updated too. Currently the ADRC only has one person that assists with website development and it is taking longer than anticipated to update the website with our request.
Goal 6: Education and Training
| The SAT will work with the Alzheimer's Association to hold one joint brain health awarness event during the month of June. | In June 2024, the SAT in partnership with the Alzheimer's Assoication to host a brain health awarness event on one of the islands | SAT and Alzheimer's will provide educational opportunities for the public to learn about brain health and bring awarness to brain health awarness month. | Amelia | Amelia is working with the Kauai Alzheimer's Assoication Chapter to hold a brain heatlh awarness event on Kauai on June 26. The event will be at Kukui Grove Mall. We will have vendors and have interactive activities such as puzzles, games, physical exercise activities for people to participate in.
Goal 7: Future Planning
| By June 2024, the SAT will identify one ACL grant to apply for that continues the work the SAT has started. | We are no longer targeting this. Another agency part of the SAT has received a Community Care grant to continue on with the NTG training and education on dementia. | Based on NTG post survey results and SAT input, we will apply for an ACL grant to continue to support the Alzheimer's and Related Dementia Diseases eduation for the state of Hawaii | Amelia
Quarter | Potential Obstacles and Notes: It has taken longer than expected for the dementia care booklet feedback to be submitted to Amelia. Therefore it might not be finalized before the end of June.
| Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #4: July, August, September 2024 | Goal One: Marketing/Educational Item
| Step 1: FRIDGE MAGNETS: By October 2024, the 1400 fridge magnets will have been distributed statewide. |  | to continue to distribute magnets each year of the grant. To ensure people know to go to the ADRC for information | Amelia
Goal Two: Workforce Development
| Step 2: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By September 2024, at least one student intern on each island will have completed their internship. | Students will have finished their internships during the summer. We will look at the post internship survey data and look at making changes for the upcoming year. | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Up and running on Maui and Kauai. Will hopefully have additional schools on Oahu and Hawaii island by December 2023 and placements available. | Amelia
Goal Three: Website Development
| UPDATE ADRC WEBSITE: By December 2023, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2024 | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Caroline | The website is not currently the priority as it was previously for the ADRC. They do not have a dedicated staff member to maintain the website and therefore the updating is taking longer than expected.
Goal Four: Resource Booklet
| Create a resource booklet with brain health information to be distributed statewide. It will include people who are willing to do EDSD screeings, brain health and signs/symptoms to look for and questions to ask your doctor. | By September 2024, the resource booklet will be ready to be distributed statewide to agencies and families | Families, caregives and support staff are requesting addiontal information and resources for individuals with IDD and Dementia as an outcome from the NTG training. This booklet will provide them with statewide resources and information. | Amelia
Goal Five: Printable Form
| One page all about me for fridge. By June 2024, the information page will be available on the ADRC and DD Council websites. | to be completed by December 2024. It will be available on DD Council website for download and part of the resource booklets as a pull out form. | Aging individuals with IDD will have a one page document on their fridge that outlines medical information to aid in their care for emergency response. | Amelia | Is currently being finalized. We will hopefully B46:F54
Potential Obstacles and Notes:

## Year 4
Bridging IDD/Aging Grant Workplan Template
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Marketing/Educational Item
Quarter #1: October-December 2024 | Step 1: FRIDGE MAGNETS: By October 2024, the 1400 fridge magnets will have been distributed statewide. |  | to continue to distribute magnets each year of the grant. To ensure people know to go to the ADRC for information | Amelia
Goal Two: Workforce Development
| Step 2: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By September 2024, at least one student intern on each island will have completed their internship. | Students will have finished their internships during the summer. We will look at the post internship survey data and look at making changes for the upcoming year. | To create an internship program for grade 12 students that will hopefully create more DSW, for it to be implemented statewide. Up and running on Maui and Kauai. Will hopefully have additional schools on Oahu and Hawaii island by December 2023 and placements available. | Amelia
Goal Three: Website Development
| UPDATE ADRC WEBSITE: By December 2023, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2024 | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Caroline
Goal Four: Resource Booklet
| Create a resource booklet with brain health information to be distributed statewide. It will include people who are willing to do EDSD screeings, brain health and signs/symptoms to look for and questions to ask your doctor. | By September 2024, the resource booklet will be ready to be distributed statewide to agencies and families | Families, caregives and support staff are requesting addiontal information and resources for individuals with IDD and Dementia as an outcome from the NTG training. This booklet will provide them with statewide resources and information. | Amelia
Goal Five: Printable Form
| One page all about me for fridge. By June 2024, the information page will be available on the ADRC and DD Council websites. | to be completed by December 2024. It will be available on DD Council website for download and part of the resource booklets as a pull out form. | Aging individuals with IDD will have a one page document on their fridge that outlines medical information to aid in their care for emergency response. | Amelia | Is currently being finalized. We will hopefully B46:F54
Potential Obstacles and Notes:
Quarter 2: January- March 2025 | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Workforce Development
| HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By March 2025, we will have identified at least one location on Hawaii island that will take student interns and will promote the internship program in Hawaii Island high schools | Starting in January 2025, we will start contacting potential adult day health programs for interns to attend. | To increase the number of DSW and knoweldge around adults with IDD within the community. To expand the project to also include Hawaii Island. | Amelia
Goal Two: Website Development
| UPDATE ADRC WEBSITE: By December 2024, the ADRC website will have a disabilities tile, and the resources the SAT created up on their website. | to have the ADRC website updated with new resources by December 2024 | SAT group sent ADRC list of resources they wanted added to the website. To increase access to available resources | Amelia/Daintry/Caroline/Cristina
Goal Three: Product Promotion
| Promote the use and signing up of inviduals with IDD and who are aging in to the SMART911 system. | to create materials (infographic) and public service announcement about the SMART911 service available. | To have individuals with IDD and kupuna sign up for the SMART 911 system so that there information comes up when they or someone from their household calls. It will provide first responders information about the individual and give them a photo. | Amelia | Using the grant funds to create and promote the use of the smart911 system for kupuna and individuals with IDD across multiple platforms.
Potential Obstacles and Notes:
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Marketing/Educational Item
Quarter #3: April-June 2025 | Step 1: FRIDGE MAGNETS: By April 2024, we will purchase an additional 1000 fridge magnets for distribution statewide. | By June 2025, we will have purchased a total of 2500 fridge magnets and will distribute them. | To increase the public's awarness and knoweldge about the ADRC website and agency as a resource for aging and disability supports. | Amelia
Goal Two: Workforce Development
| Step 2: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By September 2024, at least one student intern on each island will have completed their internship. | At least four students will be ready to start their internships at adult day health centers for the summer. | To increase the number of DSW and knoweldge around adults with IDD within the community. To expand the project to also include Hawaii Island. | Amelia
Goal Three: Product Promotion
| Step 3: Promote the use and signing up of inviduals with IDD and who are aging in to the SMART911 system. | to have the infographic about the SMART911 system created and ready for distribution by June 2025. To have an idea of what we want the public service announcement to say about the SMART911 service and work with Olelo media to record and play the public service announcement. | To have individuals with IDD and kupuna sign up for the SMART 911 system so that there information comes up when they or someone from their household calls. It will provide first responders information about the individual and give them a photo. | Amelia
Potential Obstacles and Notes:
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Goal One: Marketing/Educational Item
Quarter #4: July-September 2025 | Step 1: FRIDGE MAGNETS: By October 2024, the 1400 fridge magnets will have been distributed statewide. | All current purchased fridge magnets will have been distributed by December 2024. | To increase the public's awarness and knoweldge about the ADRC website and agency as a resource for aging and disability supports. | Amelia
Goal Two: Workforce Development
| Step 2: HIGH SCHOOL INTERNSHIP PROGRAM- INCREASE DIRECT SUPPORT WORKERS: By September 2025, at least one student intern on each island will have completed their internship. | At least four students will have completed their summer internship. | To increase the number of DSW and knoweldge around adults with IDD within the community. To expand the project to also include Hawaii Island. | Amelia
Goal Three: Product Promotion
| Step 3: Promote the use and signing up of inviduals with IDD and who are aging in to the SMART911 system. | To have Olelo media promote the use of the smart911 system through the public service announcement that has been created. | To have individuals with IDD and kupuna sign up for the SMART 911 system so that there information comes up when they or someone from their household calls. It will provide first responders information about the individual and give them a photo. | Amelia
Potential Obstacles and Notes:

## Year 5
Bridging IDD/Aging Grant Workplan Template
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #1:
Potential Obstacles and Notes:
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #2:
Potential Obstacles and Notes:
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #3:
Potential Obstacles and Notes:
Quarter | Steps/Activities: | Timeline | Expected Outcome | Person/Area Responsible | Comments
Quarter #4:
Potential Obstacles and Notes: